## Sheet1
Project Title: Minesweeper the web app
User Stories
ID | Feature | User Story | As a(n) <actor> | I would like to <description> | So that <outcome> | Priority | Sign-off Date | Modification Date
1 | FR1 | 1 | Developer | Generate this weeks burndown chart | We have a working template for future weeks | low | 2020-09-20
2 | FR1 | 2 | Developer | Outline scrum ceremonies and establish a good working time that works for all team members. This incudes planning, standups and retros. | We have established times to meet and discuss project work | low | 2020-09-20
3 | FR1 | 3 | Developer | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint | moderate | 2020-09-20
4 | FR2 | 4 | Developer | write the required stories for FR2 registration page | we have a clear idea of the requirements needed to complete the work and can assign and prioritize in nex weeks planning | high | 2020-09-20
5 | FR3 | 5 | Developer | write the required stories for FR3 Login Page | We have a clear idea of the requirements needed to complete the work and can assign and prioritize in nex weeks planning | high | 2020-09-20
6 | FR2 | 6 | Developer | create a wireframe for the registration page | so we have a viusal representation of the page we're trying to design | high | 2020-09-20
7 | FR3 | 7 | Developer | create a wireframe for the login page | so we have a viusal representation of the page we're trying to design | high | 2020-09-20
8 | FR1 | 8 | Developer | review scope docs | to understand high level requirements for the scope of this project. | high | 2020-09-20
9 | FR2 | 9 | Developer | create a registration page | so a new player can register with the game to play | low | 2020-09-27
10 | FR2 | 10 | Developer | update playerStats to a model | so we can generate a registraion page from the model | low | 2020-09-27
11 | FR2 / DB Integration | 11 | Developer | persist registration info to localDB | so we can retrieve player information for later use | low | 2020-10-04
12 | FR2 / FR3 | 12 | Developer | create a successful landing page for both registration and login | so we can let our players not they request was successful | low | 2020-09-27
13 | FR3 | 13 | Developer | Create login page | so an existing player an log in to play a new game | low | 2020-10-04
14 | FR2 / FR3 / FR4 | 14 | Developer | ServiceDOA | so we can persist data securly | low | 2020-10-11
15 | FR2 | 15 | Developer | UserService | Help persist data in to DB | high | 2020-09-27
16 | FR3 | 16 | Developer | UserLogin | Template for user login page | high | 2020-09-27
17 | FR2 / FR4 | 17 | Developer | Password entry is secure Login Page | so that we don't capture actual passwords and persist them to the DB and so that the password on entry isn't plain text | high | 2020-10-04
18 | FR1 | 18 | Team | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint | high | 2020-09-27
19 | FR1 | 19 | Team | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint | High | 2020-10-04
20 | FR2 / FR4 | 20 | Developer | Password entry is secure (Registration Page) | so that we don't capture actual passwords and persist them to the DB and so that the password on entry isn't plain text | high | 2020-10-04
21 | Fr4.5 | 21 | Developer | Create board model | so we can use existing code to create a working gameboard | high | 2020-10-04
22 | FR4.5 | 22 | Developer | Create cell model | so we can use existing code to create a working gameboard | high | 2020-10-04
23 | FR4.5 | 23 | Developer | Create GameBoardController (GBC) | A working game board to play minesweeper | high | 2020-10-04
24 | FR2/FR4 | 24 | Developer | Add validation on registration page | so we can ensure that fields are properly entered or throw errors | high | 2020-10-04
25 | FR3/FR4 | 25 | Developer | Add validation on login page | so we can ensure that fields are properly entered or throw errors | high | 2020-10-04
26 | FR4.5 | 26 | Developer | Need to populateGameBoard | This was done differently in the console and forms app, will need to rework the method to have it populate a table in a website | high | 2020-10-04
27 | FR4.5 | 27 | Developer | OnClick() for gameboard button clicks | So we can gather which button was clicked to play the game, pass the model.cell and model.row to the name which will be passed to the OnClick() method as a string | high | 2020-10-04
28 | FR4 0 FR4.5 | 28 | Team | Create week 3 user stories | So we have a scope of work defined for this week | HIgh | 2020-09-29
29 | FR4.5 | 29 | Developer | Add images folder | So we have images to use for the minesweeper game | high | 2020-10-04
30 | Fr4.5 | 30 | Developer | Create difficulty view | so we can have a player select a difficulty level before the game is created. This will also determine how many live cells there are for the game. | high | 2020-10-04
31 | FR4.5 | 31 | Developer | Add DifficultyClick() | Similar to who we read in what button is selected for the game board, do the same here. set Board.Difficulty to 33/66/99 depending on difficulty selected. View("Gameboard", board) returned. | high | 2020-10-04
32 | FR4.5 | 32 | Developer | Change landing pages | After successful log in, player should land on difficulty selection. After successful registraion, user should land on login page. | high | 2020-10-04
33 | Cleanup | 33 | Developer | remove un needed views | tech debt, some clean is required | low | 2020-10-04
34 | FR4.5 | 34 | Developer | Update board model | So we can have a global varable to set if game is over or not | high | 2020-10-18
35 | FR4.5 | 35 | Developer | update cell model | So that we have a new variable to capture right clicks to display on the game board | high | 2020-10-18
36 | FR4.5 | 36 | Team | Partial view for game over condition | When a win or loss is triggered a new partial view is needed on the bottom of the game board to ask if player wants to play again or not. | high | 2020-10-18
37 | FR4.5 | 37 | Developer | impliment win / loss logic | so our game has an end point | high | 2020-10-18
38 | FR4.5 | 38 | Developer | Right click gameboard | so we can add a flag on possible bombs | high | 2020-10-18
39 | FR2/FR3 | 39 | Developer | Add hash logic to password | so we're not storing readable passwords | high | 2020-10-18
40 | FR1 | 40 | Team | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint | high | 2020-10-18
41 | FR6 | 41 | Developer | SaveGame() endpoint | I need an endpoint I can call from the controlloer on an onclick to save the current Board to a db | high | 2020-10-25
42 |  | 42 | Developer | LoadGame() endpoing | I need an endpoing so I can load a game in progress to continue playing. | high | 2020-10-25
43 |  | 43 | Developer | GameServicesContorller | Need a new controller to handle the API calls | high | 2020-10-25
44 |  | 44 | Developer | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint | high | 2020-10-25
45 |  | 45 | Developer | New Game / Load Game view | I need a new view between login and difficulty to ask the user if they want to play a new game or load a saved game. | high | 2020-10-25
46 |  | 46 | Developer | Gametimer | I need a simple timer that increments every second to cound how long the game is played for. | high | 2020-10-25
47 |  | 47 | Developer | New dbo.Games | I need a new table to store played/saved games | high | 2020-10-25
48 |  | 48 | Developer | Add a click counter | I need a click counter to count the number of cells clicked before the game is over (win/loss) | high | 2020-10-25
49 |  | 49 | Developer | Update Views | I need a new partial view for Gameboard to be submitted through an ajax request. Update a new view to Game that displays partial views. | high | 2020-10-25
50 |  | 50 | Developer | Partial view for gameboard not showing right click till left click is clicked | UI Bug | high | 2020-11-01
51 |  | 51 | Developer | Game over partial view now showing | UI Bug | high | 2020-10-31
52 |  | 52 | Developer | Practice DI | Using unity framework, implement the logger on the login controller to practice how to implement dependency injection | high | 2020-11-01
53 |  | 53 | Developer | Update home index() | So that when the app loads, it now loads to the login screen | high | 2020-11-01
54 |  | 54 | Developer | Security filter | So that we can limit the workflow through the app forcing a user to log in before playing a game | high | 2020-11-01
55 |  | 55 | Developer | Add logging | So we have an efficient way to capture logs for the app | high | 2020-11-01
56 | FR1 | 19 | Developer | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint | low | 2020-10-11
57 | FR1 | 20 | Developer | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint | low | 2020-10-18
58 | FR1 | 21 | Developer | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint | low | 2020-10-25
59 | FR1 | 22 | Developer | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint | low | 2020-11-01
60 | FR4 | 23 | Developer | Spike needed | so we know what is expected for security concerns | Moderate | 2020-10-04
61 |  | 61 | Developer
62 |  | 62 | Developer
63 |  | 63 | Developer
64 |  | 64 | Developer
65 |  | 65 | Developer
66 |  | 66 | Developer
67 |  | 67 | Developer
68 |  | 68 | Developer
69 |  | 69 | Developer
70 |  | 70 | Developer
71 |  | 71 | Developer
72 |  | 72 | Developer
73 |  | 73 | Developer
74 |  | 74 | Developer
75 |  | 75 | Developer
76 |  | 76 | Developer
77 |  | 77 | Developer
78 |  | 78 | Developer
79 |  | 79 | Developer
80 |  | 80 | Developer
81 |  | 81 | Developer
82 |  | 82 | Developer
83 |  | 83 | Developer
84 |  | 84 | Developer
85 |  | 85 | Developer
86 |  | 86 | Developer
87 |  | 87 | Developer
88 |  | 88 | Developer
89 |  | 89 | Developer
90 |  | 90 | Developer
91 |  | 91 | Developer
92 |  | 92 | Developer
93 |  | 93 | Developer
94 |  | 94 | Developer
95 |  | 95 | Developer
96 |  | 96 | Developer
97 |  | 97 | Developer
98 |  | 98 | Developer
99 |  | 99 | Developer
100 |  | 100 | Developer
101 |  | 101 | Developer
102 |  | 102 | Developer
103 |  | 103 | Developer
104 |  | 104 | Developer
105 |  | 105 | Developer
106 |  | 106 | Developer