## Use Case Template
Project Title:FR1 Release #:1 Sprint #:1
User Stories
ID | Feature | As a(n) <actor> | I would like to <description> | So that <outcome> | Estimate | Assigned To
1 | FR1 | Developer | Generate this weeks burndown chart | We have a working template for future weeks | 1 | Matt Sievers
2 | FR1 | Developer | Outline scrum ceremonies and establish a good working time that works for all team members. This incudes planning, standups and retros. | We have established times to meet and discuss project work | 1 | Matt Sievers / Crystal Sciarrino
3 | FR1 | Team | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint | 3 | Matt Sievers / Crystal Sciarrino
4 | FR2 | Developer | write the required stories for FR2 registration page | we have a clear idea of the requirements needed to complete the work and can assign and prioritize in nex weeks planning | 1 | Matt Sievers
5 | FR3 | Developer | write the required stories for FR3 Login Page | We have a clear idea of the requirements needed to complete the work and can assign and prioritize in nex weeks planning | 1 | Matt Sievers
6 | FR2 | Developer | create a wireframe for the registration page | so we have a viusal representation of the page we're trying to design | 2 | Crystal Sciarrino
7 | FR3 | Developer | create a wireframe for the login page | so we have a viusal representation of the page we're trying to design | 2 | Crystal Sciarrino
8 | FR1 | Developer | review scope docs | to understand high level requirements for the scope of this project. | 2 | Matt Sievers / Crystal Sciarrino
9 | FR2 | Developer | create a registration page | so a new player can register with the game to play | 2 | Crystal Sciarrino
10 | FR2 | Developer | create plaer model | so we can generate a registraion page from the model | 1 | Matt Sievers
11 | FR2 / DB Integration | Developer | persist registration info to localDB | so we can retrieve player information for later use | 3 | Matt Sievers
12 | FR2 / FR3 | Developer | create a successful landing page for both registration and login | so we can let our players know their request was successful | 1 | Crystal Sciarrino
13 | FR3 | Developer | Create login page | so an existing player can log in to play a new game | 2 | Crystal Sciarrino
14 | FR2 / FR3 / FR4 | Developer | ServiceDOA | so we can persist data securly | 2 | Matt Sievers
15 | FR-2 | Developer | UserService | so we can create a new user and persist data to DB | 2 | Matt Sievers
16 | FR-3 | Developer | userLogin | Create userLogin model to help create template page for login | 1 | Matt Sievers
17 | FR4 / FR3 | Developer | Password entry is secure (Login Page) | So that we don't capture actual passwords and persist them to the DB and so that the password on entry isn't plain text | 4 | Crystal Sciarrino
18 | FR1 | Team | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint | 2 | Matt Sievers / Crystal Sciarrino
19 | FR1 | Team | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint | 2 | Matt Sievers / Crystal Sciarrino
20 | FR2 / FR4 | Developer | Password entry is secure (Registration Page) | so that we don't capture actual passwords and persist them to the DB and so that the password on entry isn't plain text |  | Crystal Sciarrino
21 | FR4.5 | Developer | Create board model | so we can use existing code to create a working game board | 1 | Matt Sievers
22 | FR4.5 | Developer | Create Cell model | so we can use existing code to create a working game board | 1 | Matt Sievers
23 | FR4.5 | Developer | Create GameBoardController (GBC) | To use existing code from CST227 to create a working game baord to play minesweekper | 4 | Matt Sievers
24 | FR2 / FR4 | Developer | Add validation on registration page | so we can ensure the fields are properly entered or throw errors | 4 | Crystal Sciarrino
25 | FR3 / FR4 | Developer | Add validation on login page | so we can ensure the fields are properly entered or throw errors | 2 | Crystal Sciarrino
26 | FR4.5 | Developer | Need to populateGameBoard. | This was done differently in the console and forms app, will need to rework the method to have it populate a table in a website | 2 | Matt Sievers
27 | FR4.5 | Developer | OnClick() for GameBoard button clicks | So we can gather which button was clicked to play the game, pass the model.cell and model.row to the name which will be passed to the OnClick() method as a string | 2 | Matt Sievers
28 | FR4 FR4.5 | Team | Create this Week 3 user stories | so we have a scope of work defineed for this weeks work. | 1 | Matt Sievers / Crystal Sciarrino
29 | FR4.5 | Developer | Add images folder | so we have images to use for the minesweeper game | 1 | Matt Sievers
30 | FR4.5 | Developer | Create a difficulty view | so we can have a player select a difficulty level before the game is created. This will also determine how many live cells there are for the game. | 1 | Matt Sievers
31 | FR4.5 | Developer | Add DifficultyClick() to GBC | Similar to who we read in what button is selected for the game board, do the same here. set Board.Difficulty to 33/66/99 depending on difficulty selected. View("Gameboard", board) returned. | 2 | Matt Sievers
32 | FR4.5 | Developer | Change landing page | After successful log in, player should land on difficulty selection. After successful registraion, user should land on login page. |  | Crystal Sciarrino
33 | Cleanup | Developer | Remove any unused success views | Technical debt, these are no longer needed | 1 | Crystal Sciarrino
34 | FR4.5 | Developer | Update board model | So we can have a global varable to set if game is over or not | 1 | Matt Sievers
35 | FR4.5 | Developer | Update cell model | So that we have a new variable to capture right clicks to display on the game board | 1 | Matt Sievers
36 | FR4.5 | Team | Partial view for game over condition | When a win or loss is triggered a new partial view is needed on the bottom of the game board to ask if player wants to play again or not. | 2 | Matt Sievers / Crystal Sciarrino
37 | FR4.5 | developer | impliment win / loss logic | so our game has an end point | 2 | Matt Sievers
38 | FR4.5 | developer | Right click gameboard | so we can add a flag on possible bombs | 8 | Matt Sievers
39 | FR2/FR3 | Developer | Add hash logic to password | so we're not storing readable passwords | 6 | Crystal Sciarrino
40 | FR1 | Team | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint | 2 | Matt Sievers / Crystal Sciarrino
41 | FR-6 | Developer | SaveGame() endpoint | I need an endpoint I can call from the controlloer on an onclick to save the current Board to a db | 6 | Matt Sievers
42 | FR-6 | Developer | LoadGame() endpoing | I need an endpoing so I can load a game in progress to continue playing. | 4 | Matt Sievers
43 | FR-6 | Developer | GameServicesContorller | Need a new controller to handle the API calls | 3 | Matt Sievers
44 | FR1 | Team | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint | 2 | Matt Sievers / Crystal Sciarrino
45 | FR-6 | Developer | New Game / Load Game view | I need a new view between login and difficulty to ask the user if they want to play a new game or load a saved game. | 1 | Matt Sievers
46 | FR-4.5 | Developer | Gametimer | I need a simple timer that increments every second to cound how long the game is played for. | 2 | Matt Sievers
47 | FR-6 | Developer | New dbo.Games | I need a new table to store played/saved games | 1 | Matt Sievers
48 | FR-4.5 | Developer | Add a click counter | I need a click counter to count the number of cells clicked before the game is over (win/loss) | 3 | Crystal Sciarrino
49 | FR-4.5 | Developer | Update Views | I need a new partial view for Gameboard to be submitted through an ajax request. Update a new view to Game that displays partial views. | 1 | Matt Sievers
50 | Bug | Developer | Partial view for gameboard not showing right click till left click is clicked | UI Bug | 4 | Crystal Sciarrino
51 | Bug | Developer | Game over partial view now showing | UI Bug | 3 | Crystal Sciarrino
52 | FR-7 | Developer | Practice DI | Using unity framework, implement the logger on the login controller to practice how to implement dependency injection | 2 | Matt Sievers
53 | FR-7 | Developer | Update home index() | So that when the app loads, it now loads to the login screen | 2 | Crystal Sciarrino
54 | FR-7 | Developer | Security filter | So that we can limit the workflow through the app forcing a user to log in before playing a game | 2 | Crystal Sciarrino
55 | FR-7 | Developer | Add logging | So we have an efficient way to capture logs for the app | 2 | Matt Sievers
56 | FR1 | Team | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint | 2 | Matt Sievers / Crystal Sciarrino
57
58