## Use Case Template
Project Title:FR1 Release #:1 Sprint #:1
User Stories
ID | Feature | As a(n) <actor> | I would like to <description> | So that <outcome> | Estimate | Assigned To
1 | FR1 | Developer | Generate this weeks burndown chart | We have a working template for future weeks | 1 | Matt Sievers
2 | FR1 | Developer | Outline scrum ceremonies and establish a good working time that works for all team members. This incudes planning, standups and retros. | We have established times to meet and discuss project work | 1 | Matt Sievers / Crystal Sciarrino
3 | FR1 | Team | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint | 3 | Matt Sievers / Crystal Sciarrino
4 | FR2 | Developer | write the required stories for FR2 registration page | we have a clear idea of the requirements needed to complete the work and can assign and prioritize in nex weeks planning | 1 | Matt Sievers
5 | FR3 | Developer | write the required stories for FR3 Login Page | We have a clear idea of the requirements needed to complete the work and can assign and prioritize in nex weeks planning | 1 | Matt Sievers
6 | FR2 | Developer | create a wireframe for the registration page | so we have a viusal representation of the page we're trying to design | 2 | Crystal Sciarrino
7 | FR3 | Developer | create a wireframe for the login page | so we have a viusal representation of the page we're trying to design | 2 | Crystal Sciarrino
8 | FR1 | Developer | review scope docs | to understand high level requirements for the scope of this project. | 2 | Matt Sievers / Crystal Sciarrino
9 | FR2 | Developer | create a registration page | so a new player can register with the game to play
10 | FR2 | Developer | update playerStats to a model | so we can generate a registraion page from the model
11 | FR2 / DB Integration | Developer | persist registration info to localDB | so we can retrieve player information for later use
12 | FR2 / FR3 | Developer | create a successful landing page for both registration and login | so we can let our players not they request was successful
13 | FR2 / FR4 | Developer | Password entry is secure | so that we don't capture actual passwords and persist them to the DB and so that the password on entry isn't plain text
14 | FR3 | Developer | Create login page | so an existing player an log in to play a new game
15 | FR2 / FR3 / FR4 | Developer | ServiceDOA | so we can persist data securly
16 | FR3 | Developer | Password entry is secure | So that we don't capture actual passwords and persist them to the DB and so that the password on entry isn't plain text
17 | FR1 | Team | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint
18 | FR1 | Team | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint
19 | FR1 | Team | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint
20 | FR1 | Team | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint
21 | FR1 | Team | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint
22 | FR1 | Team | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint
23 | FR4 | Developer | Spike needed | so we know what is expected for security concerns
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46