## Week 1
Project Title: FR-1 Release #: 1 Sprint #: 1
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
| 1 | As a developer I would like to generate this weeks burn down chart | Task 1 | Matt Sievers | 1 | 0 | 0 | 1 | 0 | 0
| 2 | As a Team I would like to outline scrum ceremoneis and set times for each | Task 2 | Matt Sievers, Crystal Sciarrino | 1 | 0 | 0 | 0 | 1 | 0
| 3 | As a team, the weekly team paperwork deliverables need to be completed | Task 3 | Matt Sievers, Crystal Sciarrino | 3 | 0 | 0 | 3 | 0 | 0
| 4 | As a developer I need to write the required user stories for FR-2 Registration page | Task 4 | Matt Sievers | 1 | 0 | 0 | 1 | 0 | 0
| 5 | As a developer I need to write the required user stories for FR-3 Login page | Task 5 | Matt Sievers | 1 | 0 | 0 | 1 | 0 | 0
| 6 | As a developer I need to create a wireframe for FR-2 Registration page for general design and layout | Task 6 | Crystal Sciarrino | 2 | 0 | 0 | 1 | 1 | 0
| 7 | As a developer I need to create a wireframe for FR-3 Login page for general design and layout | Task 7 | Crystal Sciarrino | 2 | 0 | 0 | 1 | 1 | 0
| 8 | As a team, we need to review the minesweeper code base for possible code we can reuse for this app | Task 8 | Matt Sievers | 1 | 0 | 0 | 0 | 1 | 0
| 9 | As a developer, I need to review the scope docs to understand the requirements of all FR and TR's | Task 9 | Matt Sievers/Crystal Sciarrino | 3 | 0 | 1 | 1 | 1 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 15 | 12 | 9 | 6 | 3 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 15 | 15 | 14 | 5 | 0 | 0

## Week 2
Project Title: Release #: Sprint #:
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 10
| 1 |  | Task 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 |  | Task 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 |  | Task 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 |  | Task 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5 |  | Task 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 |  | Task 6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7 |  | Task 7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8 |  | Task 8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 |  | Task 9 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Week 3
Project Title: Release #: Sprint #:
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 10
| 1 | As a developer I would like to generate this weeks burn down chart | Task 1 | Matt Sievers | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | As a developer I would like to outline scrum ceremoneis and set times for each | Task 2 | Matt Sievers | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | As a team, the weekly team paperwork deliverables need to be completed | Task 3 | Matt Sievers | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | As a developer I need to write the required user stories for FR-2 Registration page | Task 4 | Matt Sievers | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5 | As a developer I need to write the required user stories for FR-3 Login page | Task 5 | Matt Sievers | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 | As a developer I need to create a wireframe for FR-2 Registration page for general design and layout | Task 6 | Matt Sievers | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7 | As a developer I need to create a wireframe for FR-3 Login page for general design and layout | Task 7 | Matt Sievers | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8 | As a team, we need to review the minesweeper code base for possible code we can reuse for this app | Task 8 | Matt Sievers | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 | As a developer, I need to review the scope docs to understand the requirements of all FR and TR's | Task 9 | Matt Sievers | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 11 | 9.9 | 8.8 | 7.7 | 6.6 | 5.5 | 4.4 | 3.3 | 2.2 | 1.1 | 1.7764e-15
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 11 | 11 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5

## How To Use
Step 1 | Hold a Sprint Planning meeting on Day 1 of of your Sprint where you will complete or update your User Stories as well as (re)prioritize your User Stories in your Product Back Log (ideally this should be done for the next 3-4 Sprints)
Step 2 | Copy the User Stories you plan to complete for this Sprint into your Sprint Back Log
Step 3 | Copy the User Stories you plan to complete from your Sprint Back Log into Column C
Step 4 | Break the User Story into a series of step by step development tasks in Column D
Step 5 | Estimate the User Story (in 1, 2, 4 or 8 Effort Man Hours) in Column F and if the task is larger than 8 hours break the User Story into multiple User Stories
Step 6 | Assign the User Story to a single Team Member in Column E
Step 7 | Repeat steps 4-6 for each User Story that has been planned for this Sprint
Step 8 | At the end of each day each Team Member should update the effort hours that were worked on their User Story to burn their work down
Step 9 | After each Daily Standup each Team Member should review the Burn Down Chart to ensure your Sprint will be delivered on time