## Sheet1
Project Title: Minesweeper the web app
User Stories
ID | Feature | User Story | As a(n) <actor> | I would like to <description> | So that <outcome> | Priority | Sign-off Date | Modification Date
1 | FR1 | 1 | Developer | Generate this weeks burndown chart | We have a working template for future weeks | low | 2020-09-20
2 | FR1 | 2 | Developer | Outline scrum ceremonies and establish a good working time that works for all team members. This incudes planning, standups and retros. | We have established times to meet and discuss project work | low | 2020-09-20
3 | FR1 | 3 | Developer | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint | moderate | 2020-09-20
4 | FR2 | 4 | Developer | write the required stories for FR2 registration page | we have a clear idea of the requirements needed to complete the work and can assign and prioritize in nex weeks planning | high | 2020-09-20
5 | FR3 | 5 | Developer | write the required stories for FR3 Login Page | We have a clear idea of the requirements needed to complete the work and can assign and prioritize in nex weeks planning | high | 2020-09-20
6 | FR2 | 6 | Developer | create a wireframe for the registration page | so we have a viusal representation of the page we're trying to design | high | 2020-09-20
7 | FR3 | 7 | Developer | create a wireframe for the login page | so we have a viusal representation of the page we're trying to design | high | 2020-09-20
8 | FR1 | 8 | Developer | review scope docs | to understand high level requirements for the scope of this project. | high | 2020-09-20
9 | FR2 | 9 | Developer | create a registration page | so a new player can register with the game to play | low | 2020-09-27
10 | FR2 | 10 | Developer | update playerStats to a model | so we can generate a registraion page from the model | low | 2020-09-27
11 | FR2 / DB Integration | 11 | Developer | persist registration info to localDB | so we can retrieve player information for later use | low | 2020-10-04
12 | FR2 / FR3 | 12 | Developer | create a successful landing page for both registration and login | so we can let our players not they request was successful | low | 2020-09-27
13 | FR2 / FR4 | 13 | Developer | Password entry is secure | so that we don't capture actual passwords and persist them to the DB and so that the password on entry isn't plain text | low | 2020-09-27
14 | FR3 | 14 | Developer | Create login page | so an existing player an log in to play a new game | low | 2020-10-04
15 | FR2 / FR3 / FR4 | 15 | Developer | ServiceDOA | so we can persist data securly | low | 2020-10-11
16 | FR3 | 16 | Developer | Password entry is secure | So that we don't capture actual passwords and persist them to the DB and so that the password on entry isn't plain text | low | 2020-10-04
17 | FR1 | 17 | Developer | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint | low | 2020-09-27
18 | FR1 | 18 | Developer | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint | low | 2020-10-04
19 | FR1 | 19 | Developer | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint | low | 2020-10-11
20 | FR1 | 20 | Developer | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint | low | 2020-10-18
21 | FR1 | 21 | Developer | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint | low | 2020-10-25
22 | FR1 | 22 | Developer | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint | low | 2020-11-01
23 | FR4 | 23 | Developer | Spike needed | so we know what is expected for security concerns | Moderate | 2020-10-04
24 |  | 24 | Developer
25 |  | 25 | Developer
26 |  | 26 | Developer
27 |  | 27 | Developer
28 |  | 28 | Developer
29 |  | 29 | Developer
30 |  | 30 | Developer
31 |  | 31 | Developer
32 |  | 32 | Developer
33 |  | 33 | Developer
34 |  | 34 | Developer
35 |  | 35 | Developer
36 |  | 36 | Developer
37 |  | 37 | Developer
38 |  | 38 | Developer
39 |  | 39 | Developer
40 |  | 40 | Developer
41 |  | 41 | Developer
42 |  | 42 | Developer
43 |  | 43 | Developer
44 |  | 44 | Developer
45 |  | 45 | Developer
46 |  | 46 | Developer
47 |  | 47 | Developer
48 |  | 48 | Developer
49 |  | 49 | Developer
50 |  | 50 | Developer
51 |  | 51 | Developer
52 |  | 52 | Developer
53 |  | 53 | Developer
54 |  | 54 | Developer
55 |  | 55 | Developer
56 |  | 56 | Developer
57 |  | 57 | Developer
58 |  | 58 | Developer
59 |  | 59 | Developer
60 |  | 60 | Developer
61 |  | 61 | Developer
62 |  | 62 | Developer
63 |  | 63 | Developer
64 |  | 64 | Developer
65 |  | 65 | Developer
66 |  | 66 | Developer
67 |  | 67 | Developer
68 |  | 68 | Developer
69 |  | 69 | Developer
70 |  | 70 | Developer
71 |  | 71 | Developer
72 |  | 72 | Developer
73 |  | 73 | Developer
74 |  | 74 | Developer
75 |  | 75 | Developer
76 |  | 76 | Developer
77 |  | 77 | Developer
78 |  | 78 | Developer
79 |  | 79 | Developer
80 |  | 80 | Developer
81 |  | 81 | Developer
82 |  | 82 | Developer
83 |  | 83 | Developer
84 |  | 84 | Developer
85 |  | 85 | Developer
86 |  | 86 | Developer
87 |  | 87 | Developer
88 |  | 88 | Developer
89 |  | 89 | Developer
90 |  | 90 | Developer
91 |  | 91 | Developer
92 |  | 92 | Developer
93 |  | 93 | Developer
94 |  | 94 | Developer
95 |  | 95 | Developer
96 |  | 96 | Developer
97 |  | 97 | Developer
98 |  | 98 | Developer
99 |  | 99 | Developer
100 |  | 100 | Developer
101 |  | 101 | Developer
102 |  | 102 | Developer
103 |  | 103 | Developer
104 |  | 104 | Developer
105 |  | 105 | Developer
106 |  | 106 | Developer
107 |  | 107 | Developer
108 |  | 108 | Developer
109 |  | 109 | Developer
110 |  | 110 | Developer
111 |  | 111 | Developer