## Use Case Template
Project Title:FR1 Release #:1 Sprint #:1
User Stories
ID | Feature | As a(n) <actor> | I would like to <description> | So that <outcome> | Estimate | Assigned To
1 | FR1 | Developer | Generate this weeks burndown chart | We have a working template for future weeks | 1 | Matt Sievers
2 | FR1 | Developer | Outline scrum ceremonies and establish a good working time that works for all team members. This incudes planning, standups and retros. | We have established times to meet and discuss project work | 1 | Matt Sievers / Crystal Sciarrino
3 | FR1 | Team | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint | 3 | Matt Sievers / Crystal Sciarrino
4 | FR2 | Developer | write the required stories for FR2 registration page | we have a clear idea of the requirements needed to complete the work and can assign and prioritize in nex weeks planning | 1 | Matt Sievers
5 | FR3 | Developer | write the required stories for FR3 Login Page | We have a clear idea of the requirements needed to complete the work and can assign and prioritize in nex weeks planning | 1 | Matt Sievers
6 | FR2 | Developer | create a wireframe for the registration page | so we have a viusal representation of the page we're trying to design | 2 | Crystal Sciarrino
7 | FR3 | Developer | create a wireframe for the login page | so we have a viusal representation of the page we're trying to design | 2 | Crystal Sciarrino
8 | FR1 | Developer | review scope docs | to understand high level requirements for the scope of this project. | 2 | Matt Sievers / Crystal Sciarrino
9 | FR2 | Developer | create a registration page | so a new player can register with the game to play | 2 | Crystal Sciarrino
10 | FR2 | Developer | create plaer model | so we can generate a registraion page from the model | 1 | Matt Sievers
11 | FR2 / DB Integration | Developer | persist registration info to localDB | so we can retrieve player information for later use | 3 | Matt Sievers
12 | FR2 / FR3 | Developer | create a successful landing page for both registration and login | so we can let our players know their request was successful | 1 | Crystal Sciarrino
13 | FR3 | Developer | Create login page | so an existing player can log in to play a new game | 2 | Crystal Sciarrino
14 | FR2 / FR3 / FR4 | Developer | ServiceDOA | so we can persist data securly | 2 | Matt Sievers
15 | FR-2 | Developer | UserService | so we can create a new user and persist data to DB | 2 | Matt Sievers
16 | FR-3 | Developer | userLogin | Create userLogin model to help create template page for login | 1 | Matt Sievers
17 | FR4 | Developer | Password entry is secure | So that we don't capture actual passwords and persist them to the DB and so that the password on entry isn't plain text
18 | FR1 | Team | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint | 2 | Matt Sievers / Crystal Sciarrino
19 | FR1 | Team | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint
20 | FR1 | Team | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint
21 | FR1 | Team | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint
22 | FR1 | Team | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint
23 | FR1 | Team | ensure that the weekly team paperwork is filled out for submission. | nothing is missed at completion of sprint
24 | FR4 | Developer | Spike needed | so we know what is expected for security concerns
25 | FR2 / FR4 | Developer | Password entry is secure | so that we don't capture actual passwords and persist them to the DB and so that the password on entry isn't plain text
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47