## Week 1
Project Title: FR-4 FR-4.5 Release #: 3 Sprint #: 3
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
| 17 | As a developer, I need to update the regisration page password to show *** | Task 17 | Crystal Sciarrino | 0 | 0 | 0 | 0 | 0 | 0
| 19 | As a team, the weekly team paperwork deliverables need to be completed | Task 19 | Matt Sievers/Crystal Sciarrino | 2 | 0 | 0 | 0 | 1 | 0
| 20 | As a developer, I need to update the Login page password to show *** | Task 20 | Crystal Sciarrino | 0 | 0 | 0 | 0 | 0 | 0
| 21 | As a developer I need to create the board model | Task 21 | Matt Sievers | 1 | 0 | 1 | 0 | 0 | 0
| 22 | As a developer I need to create the cell model | Task 22 | Matt Sievers | 1 | 0 | 1 | 0 | 0 | 0
| 23 | As a developer I need to create the GameBoardController *(GBC) | Task 23 | Matt Sievers | 4 | 0 | 3 | 1 | 0 | 0
| 24 | Ass a developer I need to add validation to the models for entry on the registration page | Task 24 | Crystal Sciarrino | 0 | 0 | 0 | 0 | 0 | 0
| 25 | Ass a developer I need to add validation to the models for entry on the Login page | Task 25 | Crystal Sciarrino | 0 | 0 | 0 | 0 | 0 | 0
| 26 | As a developer, I need to update GBC to populate and build the game baord into a 2d array to use ina table on the view | Task 26 | Matt Sievers | 2 | 0 | 1 | 1 | 0 | 0
| 27 | As a developer, I need an OnClick() method to help determine which button was clicked on the game board. Add simple logic to add a bomb image for live==true and if not show neighbors value (if 0 "") | Task 27 | Matt Sievers | 2 | 0 | 0 | 2 | 0 | 0
| 28 | As a team, we need to create week 3 user stories | Task 28 | Matt Sievers/Crystal Sciarrino | 1 | 1 | 0 | 0 | 0 | 0
| 29 | As a developer, I need a new folder to house images used for the game | Task 29 | Matt Sievers | 1 | 0 | 1 | 0 | 0 | 0
| 30 | As a developer I need a new view created to select difficulty. Three buttons, easy, moderate, hard are required to set the game baord live cells. | Task 30 | Matt Sievers | 1 | 0 | 0 | 1 | 0 | 0
| 31 | As a developer, I need to add the DifficultyClick() to GBC. | Task 31 | Matt Sievers | 2 | 0 | 0 | 2 | 0 | 0
| 32 | As a developer, I need to update the workflow so that the registrationa nd login pages land on the right pages now. Registration -> Login -> Difficulty | Task 32 | Crystal Sciarrino | 0 | 0 | 0 | 0 | 0 | 0
| 33 | As a developer, I need to remove un needed views. | Task 33 | Crystal Sciarrino | 1 | 0 | 0 | 0 | 1 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 18 | 14.4 | 10.8 | 7.2 | 3.6 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 10 | 10 | 4 | 2 | 1 | 1

## Week 2
Project Title: Release #: Sprint #:
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 10
| 1 | As a developer, I need to create a login page that will ask the user for user name and password | Task 1 | Crystal Sciarrino | 0 | 3 | 0 | 0 | 0 | 0 | 1 |  | 2 | 0 | 0
| 2 | As a developer I need to create a registration page that has the following fields. Firstname, LastName, Age, Gender, State, emailAddress, Username, Password | Task 2 | Crystal Sciarrino | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0
| 3 |  | Task 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 |  | Task 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5 |  | Task 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 |  | Task 6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7 |  | Task 7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8 |  | Task 8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 |  | Task 9 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 0 | -6 | -6 | -6 | -6 | -6 | -8 | -8 | -12 | -12 | -12

## Week 3
Project Title: Release #: Sprint #:
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 10
| 1 | As a developer I would like to generate this weeks burn down chart | Task 1 | Matt Sievers | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | As a developer I would like to outline scrum ceremoneis and set times for each | Task 2 | Matt Sievers | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | As a team, the weekly team paperwork deliverables need to be completed | Task 3 | Matt Sievers | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | As a developer I need to write the required user stories for FR-2 Registration page | Task 4 | Matt Sievers | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5 | As a developer I need to write the required user stories for FR-3 Login page | Task 5 | Matt Sievers | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 | As a developer I need to create a wireframe for FR-2 Registration page for general design and layout | Task 6 | Matt Sievers | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7 | As a developer I need to create a wireframe for FR-3 Login page for general design and layout | Task 7 | Matt Sievers | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8 | As a team, we need to review the minesweeper code base for possible code we can reuse for this app | Task 8 | Matt Sievers | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 | As a developer, I need to review the scope docs to understand the requirements of all FR and TR's | Task 9 | Matt Sievers
| 10 | As a developer, I need to update the registration page password to show *** | Task 10 | Crystal Sciarrino | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 11 | As a developer, I need to update the Login page password to show *** | Task 11 | Crystal Sciarrino | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 12 | As a developer I need to add validation to the models for entry on the registration page | Task 12 | Crystal Sciarrino | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| 13 | As a developer I need to add validation to the models for entry on the Login page | Task 13 | Crystal Sciarrino | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 14 | As a developer, I need to update the workflow so that the registration and login pages land on the right pages now. Registration -> Login -> Difficulty | Task 14 | Crystal Sciarrino | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| 15 | As a developer, I need to remove un needed views. | Task 15 | Crystal Sciarrino | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 10 | 10 | 10 | 0 | -5 | -6 | -7 | -7 | -7 | -7 | -7

## How To Use
Step 1 | Hold a Sprint Planning meeting on Day 1 of of your Sprint where you will complete or update your User Stories as well as (re)prioritize your User Stories in your Product Back Log (ideally this should be done for the next 3-4 Sprints)
Step 2 | Copy the User Stories you plan to complete for this Sprint into your Sprint Back Log
Step 3 | Copy the User Stories you plan to complete from your Sprint Back Log into Column C
Step 4 | Break the User Story into a series of step by step development tasks in Column D
Step 5 | Estimate the User Story (in 1, 2, 4 or 8 Effort Man Hours) in Column F and if the task is larger than 8 hours break the User Story into multiple User Stories
Step 6 | Assign the User Story to a single Team Member in Column E
Step 7 | Repeat steps 4-6 for each User Story that has been planned for this Sprint
Step 8 | At the end of each day each Team Member should update the effort hours that were worked on their User Story to burn their work down
Step 9 | After each Daily Standup each Team Member should review the Burn Down Chart to ensure your Sprint will be delivered on time